## Test Plan
Reviewer Name: | Valerie Rudich, Constance Sturm
Date of Review: | 2023-11-07
Item Reviewed: | Test Plan
Criteria | Met Standards? Yes/No | Additional Information
Does the plan list the Test Scope? | Yes | The plan clearly states what aspects of the application will be tested.
Does the plan list the Test Approach? | Yes | States how the team will approach testing before deployment
Does the plan list Test Types? | Yes | The plan shows that we will use manual testing.
Does the plan list Input/Output? | Yes | The plan shows in the table the User's input and what the expected output will be.
Does the plan discuss Regression Tests? | Yes | States in defect resolution section that code will be retested after errors are corrected. The code will also be tested after each addition for any bugs.
Does the plan discuss Defect Management? | Yes | The test plan states what the team will do for defect documentation and logging. The test plan also states how we will resolve the defects that were found.
Is the plan well organized? | Yes | The plan is very organized and easy to find information about what is being tested.
Is the plan free of grammer and spelling errors? | Yes | These documents were reviewed by the team for grammer and spelling errors.

## User Guide
Reviewer Name: | Valerie Rudich, Constance Sturm
Date of Review: | 2023-11-07
Item Reviewed: | User Guide
Criteria | Met Standards? Yes/No | Additional Information
Does this version contain the basic skeleton of the program? | Yes | Explained using plain english and a mockup of the program screens was also created to help understand what the program will be able to do/how it will work.
Does this version demonstrate the key user functions? | Yes | The user guide shows how the user can utilize the program.
Is the user guide well organized? | Yes | The guide is well organized with guiding the user on how to use the application.
Is the plan free of grammer and spelling errors? | Yes | The team has reviewed the documents for grammer and spelling errors.

## Phase 1
Reviewer Name: | Constance Sturm
Date of Review: | 2023-11-21
Item Reviewed: | Phase 1 of Source Code/.txt Files
Criteria |  | Notes
Does the source code match the design plan? | Yes | The source code follows the design plan.
Is the source code complete? | No | The source code needs one more prompt and the rules added to the code.
Are the .txt files complete? | No | The .txt files need more fortunes added.
Any changes that may be implemented? | Yes | One of the fortune categories may be changed from health to a different topic. Further discussion needed.
Any changes to the test plan? | Yes | If the fortune category changes the test plan will change slightly to show this new category. The actual flow of the test plan will not change.
Any changes to the design plan? | Yes | If the fortune category changes the design plan will change slightly to show this new category. The flow of the design plan will not change.
Is the plan well organized? | Yes | The code and .txt files are still organized on what needs to be added and what needs to be changed.
Is the plan free of grammer and spelling errors? | Yes | The source code and .txt files are free from gramical errors.

## Phase 2
Reviewer Name: | Chelsea Nieves, Hoi Lam Wong
Date of Review: | 2023-11-28
Item Reviewed: | Phase 2 of Source Code/.txt Files
Criteria |  | Notes
Does the source code match the design plan? | Yes | The source code follows the design plan.
Is the source code complete? | No | The front end of the GUI has predominantly been developed, and a template for the back end logic of the program has been developed. Once the GUI is operational the database code will be integrated with the GUI and tested for functionality.
Are the .txt files complete? | Yes | All .txt fortune documents have been updated with data and the format has been modified for easier reading (no longer parsing with ":")
Any changes that may be implemented? | Yes | The main menu will likely be modified for ease of use.
Any changes to the test plan? | Yes | Yes, the test plan will need to be modified to include the testing of user data stored in the database
Any changes to the design plan? | No | The design plan follows a similar flow despite the program's modification from a command line program to GUI
Is the plan well organized? | Yes | The code and .txt files are still organized on what needs to be added and what needs to be changed.
Is the plan free of grammer and spelling errors? | Yes | The source code and .txt files are free from grammatical errors.

## Future Items for Review
Reviewer Name:
Date of Review:
Item Reviewed:
Criteria | Met Standards? Yes/No | Notes
Is the plan well organized?
Is the plan free of grammer and spelling errors?

## To Do
Task | Assignee | Status
Modify GUI flow (Welcome Menu, Continue as Guest, etc.) | Constance Sturm
Validate registration | Hoi Lam | Password is being validated. Need to add actual value to database now.
Add password confirmation field to registration form | Hoi Lam | Done
Obscure password fields for login and registration form | Hoi Lam | Done
Add global variable to track user authentication status | Constance Sturm
Add if statement to control whether “Previous Fortunes” are displayed to user (Yes if authenticated, No if guest) | Constance Sturm
Implement and test database for user login/registration | Chelsea Nieves | Pending GUI form completeness to incorporate label names into db template
Implement and test database for past fortunes for account holding users | Chelsea Nieves | Pending GUI form completeness to incorporate label names into db template
Create table to store previous user fortunes | Chelsea Nieves | Working
Input validation for user login fields (username cannot be blank, etc.) | Constance Sturm